## Sheet1
1. Form Field Validations
Page Name | Form ID | Field ID | Expected Values
LogIn | user login - spotify | field ID 1 | string
Upload | Happy Pic 1 | field ID 2 | 100
Upload | Sad Pic 1 | field ID 3 | -100
Upload | Confused Pic 1 | field ID 4 | -50 ~ 0
Upload | Neutral Pic 1 | field ID 5 | 0 ~ 50
Parsed | Results 1 | field ID 6 | Average Score
2. Data Validation
Table | Field | Type | Read/Write | Data Source | Constraints | TestID | Pass/Fail
User | Login field | Login | Write | write.mongo | string | testID1 | P
User.Score | Score field | Analysis & Calculate | Write | write.mongo | int | testID2 | P
User.Score | Score field | Analysis & Calculate | Write | write.mongo | int | testID3 | P
User.Score | Score field | Analysis & Calculate | Write | write.mongo | int | testID4 | P
User.Score | Score field | Analysis & Calculate | Write | write.mongo | int | testID5 | P
User.Score | Score field | Calculate Average | Read | read.mongo | float | testID6 | F
3. UI Validation
Page Name | UI Element | Expected Function | Test ID | Pass/Fail
LogIn - About | Start Button | Log-In - Redirect | testID1 | P
Take Picture | Button | Takes picture | testID2 | F
Upload Picture | Button | select picture from directory | testID3 | P
Send Picture | Button | send picture for processing | testID4 | P
Go to Spotify | Button | link redirect | testID5 | F
4. Remediation
BugID | TestID | Description |  |  |  | Severity (1-3) | Assigned | Completed Date
NanScore | testID6 - pt2 | When all the previous scores are nan values, the average is nan. |  |  |  | 1 | Seung Hee | Dec 7th 2018
TakePicture | testID2 - pt3 | Does not save the picture in the designated folder. |  |  |  | 1 | Hayato | Dec 7th 2018
SpotifyToken | testID5 - pt3 | Spotify Token is not saved every time. |  |  |  | 3 | Ziyao | Dec 6th 2018